## Risk_Register
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence/Impact | Likelihood Score | Impact Score | Risk Score | Priority (H, M, L) | Mitigation | Risk Owner | Open/Closed
1 | 2026-03-03 | Cybersecurity breach or ransomware event disrupts RPM monitoring and exposes patient data | Expansion of IoT‑connected RPM devices, cloud-based vendor platforms, and increased endpoints (attack surface) in the RPM ecosystem | Service downtime, delayed clinical escalation, potential privacy breach, reputational damage and reduced RPM adoption | Operational disruption to monitoring workflows; legal/compliance exposure under BC/Canadian privacy requirements; recovery/remediation costs; loss of patient/provider trust and competitive disadvantage versus private digital health providers | 3 | 5 | 15 | H | Zero‑trust access controls (MFA/least privilege), encryption in transit/at rest, continuous vulnerability management & patch SLAs, device/vendor security reviews, ransomware playbook + backups and incident response drills, staff phishing training | Chief Information Security Officer (CISO) / Digital Health | Open
2 | 2026-03-03 | Opportunity to strengthen Fraser Health’s digital health leadership through rapid scaling of RPM | Rising demand for remote monitoring and chronic care support, plus system pressure to shift care from hospital to home | Higher RPM adoption, improved outcomes, and efficiency gains—creating competitive advantage in BC’s digital health ecosystem | Operational: fewer avoidable admissions and better capacity management; financial: improved resource efficiency and stronger case for sustained funding; strategic: enhanced reputation as a digital health leader and higher stakeholder confidence | 4 | 5 | 20 | H | Scale eligibility cohorts and enrollment capacity, secure device supply/vendor SLAs, integrate RPM into care pathways/EMR, invest in analytics for early deterioration detection, track equity access (rural/underserved) and adjust deployment | Chief Medical Information Officer (CMIO) / Digital Innovation | Open
3 | 2026-03-03 | Reliance on a single RPM vendor limits Fraser Health’s ability to adopt more competitive solutions | Vendor lock-in due to long-term contracts and proprietary systems | Reduced flexibility to integrate new technologies or switch vendors | Higher operational costs and slower response to market innovation | 3 | 3 | 9 | M | Use multi-vendor strategies, negotiate flexible contracts, and adopt interoperable standards for RPM platforms | Procurement & Digital Health Technology Team | Open